## Overview
Dobby — Expansion to a Local-First AI Workbench
12-month plan · feature specs · roadmap · effort · budget · resources · market. All figures are illustrative planning estimates.
Vision | Capture → Generate → Automate → Build → Ship — one minimal, categorized, local-first app with a marketplace of skills/flows/apps.
Timeline | 6 phases over 12 months (P1 Foundations → P6 Publish & Cloud).
Build effort | ~247 person-weeks; team scaling 3 → 6.
Funding ask | $2,200,000 seed · 18 months runway.
12-mo operating plan | $1,134,200 (Base). Scenarios: Lean $720,000 · Base $1,134,200 · Ambitious $1,720,000
Market | TAM $48,000,000,000 · SAM $6,200,000,000 · SOM(3y) $42,000,000.
Business model | Free desktop → Pro/Team subscriptions + marketplace take-rate + optional cloud sync.
Moat | Local-first privacy + a skills/flows/apps marketplace flywheel.
Tabs: Feature Specs · Roadmap · Effort · Team & Resources · Budget · Market · Milestones

## Feature Specs
The 13 new features that turn Dobby into a local-first AI workbench.
# | Feature | Category | Phase | Size | Effort (pw) | Description | User value | Persona | Key capabilities | Architecture | Dependencies | Risks | Acceptance
1 | Global Search | System | P1 | M | 4 | Global Search indexes all Dobby artifacts (projects, the 7 generated documents, backlog items, dependency-graph nodes, notes, transcripts, and run logs) into a single local index and answers queries with a blend of SQLite FTS5 full-text ranking and local vector similarity. Embeddings are produced on-device via a small local model (e.g. nomic-embed-text or bge-small through Ollama) and stored in sqlite-vec, so nothing leaves the machine. Results are typed, de-duplicated, and grouped by category with inline snippets and match highlighting. An incremental indexer keeps the index fresh by subscribing to create/update/delete events from the existing document pipeline, so newly generated docs are searchable within seconds. | Builders instantly recall anything they have ever generated or captured without remembering which project or file it lived in. One keystroke jumps from a vague memory to the exact document, note, or run. | Solo founder | • Hybrid ranking that fuses SQLite FTS5 BM25 scores with sqlite-vec cosine similarity • On-device embedding generation via a local model with batched, cached vectors • Incremental, event-driven reindexing on document/note/run create-update-delete • Typed, category-grouped results with snippet extraction and term highlighting • Scoped filters (by project, category, date range, document type) • Keyboard-first result navigation with instant open/preview • Graceful fallback to pure full-text when no embedding model is installed | New FastAPI module src/search/ owns an indexer service and a query service; storage uses SQLite FTS5 virtual tables plus a sqlite-vec extension table for embeddings. Embeddings call the local Ollama/llama.cpp embedding endpoint with an in-process LRU cache. Tauri IPC exposes search/query and search/reindex commands; the indexer subscribes to existing pipeline events to stay incremental. | • None | • Embedding model availability varies across users; must degrade to FTS-only cleanly • Index bloat and reindex latency on large libraries without incremental batching • Hybrid score normalization can surface irrelevant vector matches if weights are untuned | • Query returns fused FTS + vector results in under 300ms on a 5k-item library • A newly generated document is searchable within 5s of creation • Results are grouped by category with correct snippet highlighting • Deleting an item removes it from both FTS and vector indexes • With no embedding model installed, search still returns full-text results without error • Scope filters correctly restrict results to the selected project or type
2 | Command Center | Automate | P1 | M | 3 | Command Center is the keyboard-driven nerve center invoked with a global shortcut from anywhere in the app. It aggregates navigation targets, generator entry points (Wizard/YOLO/Bulk), recent projects and documents, and — as later phases land — installed skills and flows into one fuzzy-searchable list of executable actions. Each action carries metadata (icon, category, argument schema) so the palette can prompt for parameters inline before dispatching to the appropriate backend command. A local usage-frequency store ranks recently and often-used actions to the top, and the same action registry powers Global Search's action results. Everything resolves against a local action registry with no network calls. | Power users drive the entire workbench from the keyboard, cutting multi-click navigation to a single palette invocation. It becomes the fastest path to start any generation or automation. | Indie developer/hacker | • Global shortcut invocation with fuzzy matching over a typed action registry • Inline argument prompts driven by each action's parameter schema • Frequency- and recency-ranked results via a local usage store • Dispatch to navigation, generators, and (later) skills and flows • Extensible action registry other modules register into at startup • Category-scoped modes (e.g. > for commands, @ for projects) • Recent-actions list and quick-repeat of the last command | New src/actions/ module maintains an in-memory action registry populated by each feature module at startup and persisted metadata in SQLite; the frontend palette is a React overlay component. Argument schemas are JSON-schema-like and validated client-side before an IPC dispatch to the target FastAPI command. Usage frequency is stored locally to rank results. | • Global Search | • Action registry fragmentation if modules register inconsistently • Argument-schema UX becomes clunky for actions with many parameters • Keybinding conflicts with OS or WebView shortcuts | • The global shortcut opens the palette from any screen and focuses the input • Fuzzy search matches action names and aliases with sub-100ms filtering • Executing a navigation action routes correctly; a generator action starts the flow • An action requiring arguments shows an inline form and validates before dispatch • Frequently used actions rise to the top across sessions • New modules can register actions without changing palette code
3 | Logs & Traces | System | P1 | M | 4 | Logs & Traces gives builders a timeline of every run in Dobby: document generations, verifier passes, skills, and flows. Each run emits a structured trace of nested spans (agent step, LLM call, tool invocation, verifier check) with timing, token counts, inputs, outputs, and status, persisted to SQLite. A live-tailing view streams spans as a run executes, and a tree/waterfall view lets users drill into any completed run to inspect prompts, model responses, and errors. Because all telemetry is local, users can debug prompt regressions and slow steps without any external observability service. | When a generation misbehaves or a flow fails, builders can see exactly which step and prompt caused it instead of guessing. It turns opaque AI runs into inspectable, debuggable timelines. | Indie developer/hacker | • Structured span model (run > agent step > LLM/tool call) with timing and token metrics • Live tailing of spans over an IPC/event stream during execution • Waterfall and tree visualizations of completed runs • Full prompt/response/tool-arg capture with expandable payload viewers • Status, error, and retry annotations per span • Filter and search runs by feature, project, status, and date • Local retention policy with size-capped pruning | New src/tracing/ module exposes a lightweight span-emitter API instrumented into the generation pipeline, verifiers, and later skills/flows; spans persist to SQLite tables (runs, spans) with JSON payload columns. A pub/sub event bus pushes span updates over Tauri IPC to the live view. A background pruner enforces retention limits. | • None | • Instrumentation overhead or payload bloat if large prompts are stored verbatim • Retrofitting span emission across existing pipeline code is invasive • Live streaming backpressure on very chatty runs | • Every document generation produces a run with nested, timed spans • Live-tail view shows spans appearing within 1s of emission • A completed run's waterfall accurately reflects span durations and order • Prompt and response payloads are viewable and correctly associated with their span • Failed spans are visibly marked with captured error detail • Retention pruning caps stored trace size without corrupting recent runs
4 | Embedded Terminal | System | P2 | M | 5 | Embedded Terminal provides an interactive shell pane backed by a real PTY, scoped to a per-project working directory. Every command — whether typed by the user or proposed by an agent/flow — runs through an approval gate with an allowlist/denylist policy, so destructive or network operations require explicit confirmation. The PTY runs in a restricted environment (constrained cwd, scrubbed env, optional command timeouts and output caps) and streams stdout/stderr into an xterm-style view. This lets automations execute build, test, and scaffold commands locally while keeping the user in control of anything risky. | Builders and their agents can run real commands (installs, builds, tests, git) without leaving Dobby, while approval gating prevents an automation from doing anything destructive unattended. | Indie developer/hacker | • Real PTY sessions scoped to a per-project working directory • Approval gate with configurable allowlist/denylist and per-command confirm • Streaming stdout/stderr into an xterm.js terminal view • Restricted environment: scrubbed env vars, cwd jail, output size caps • Per-command timeouts and a kill/abort control • Agent-proposed commands surfaced for user approval before execution • Session history persisted per project | New src/terminal/ module wraps a PTY (via a Rust pty crate in the Tauri layer or a Python pty bridge) with a policy engine evaluating each command against allow/deny rules. Sessions and history persist to SQLite; the frontend uses xterm.js fed over an IPC byte stream. The environment is constrained (cwd jail, filtered env) and every gated command requires explicit user confirmation. | • Logs & Traces | • Sandbox escape or policy bypass if command parsing is naive (shell metacharacters) • Cross-platform PTY behavior differences (macOS/Linux/Windows) • Approval fatigue if the gate fires too often for benign commands | • A typed command runs in the project cwd and streams output live • A denylisted or agent-proposed command is blocked until explicitly approved • Commands cannot read or write outside the configured cwd jail • A long-running command can be aborted and respects the configured timeout • Command approvals and executions appear as spans in Logs & Traces • Session history reloads correctly when reopening a project
5 | Audio Transcription | Studio | P2 | M | 4 | Audio Transcription lets users import audio/video files (or record directly) and produces a timestamped, speaker-segmented transcript entirely on-device using Whisper.cpp or faster-whisper. Files are decoded via a bundled ffmpeg, chunked, and transcribed with a user-selectable model size (tiny to large) to trade speed for accuracy. Progress streams per chunk, and the finished transcript is editable, searchable (via Global Search), and can be sent straight into Notes Builder. Transcripts and their segment timing are stored locally so they can be replayed against the source audio. | Creators and founders turn interviews, meetings, and voice memos into searchable text without paying for or trusting a cloud transcription service. Everything stays private and works offline. | Technical creator (YouTuber/writer) | • Local STT via Whisper.cpp or faster-whisper with selectable model size • ffmpeg-based decoding of common audio/video containers • Timestamped segments with optional speaker/diarization labels • Streaming per-chunk progress and partial transcript display • In-app recording capture as a transcription source • Editable transcript with segment-to-audio playback sync • One-click handoff to Notes Builder and indexing into Global Search | New src/studio/transcription/ module shells out to a bundled Whisper.cpp/faster-whisper binary and ffmpeg, running jobs on a background worker queue. Transcripts, segments, and job status persist to SQLite; audio files are stored in a local media directory. Progress and completion stream over Tauri IPC events; output is registered with the search indexer. | • Global Search • Logs & Traces | • Model download size and first-run setup friction for larger Whisper models • Transcription latency on CPU-only machines for long files • Diarization accuracy is limited without heavier local models | • Importing a common audio/video file produces a timestamped transcript • Users can choose a Whisper model size and see the accuracy/speed trade-off • Progress streams per chunk and partial text appears during processing • Clicking a segment seeks the audio player to that timestamp • Edited transcripts persist and are findable via Global Search • A transcript can be sent to Notes Builder in one action
6 | YouTube to Notes | Studio | P2 | M | 3 | YouTube to Notes takes a video URL, uses yt-dlp to fetch the audio stream (and any available captions) locally, then either parses existing captions or runs the audio through the Audio Transcription pipeline. The resulting transcript is passed to Notes Builder to produce structured, sectioned notes with timestamps and key takeaways. Everything downloads to and processes on the user's machine, so there is no third-party transcription or summarization service in the loop. Source metadata (title, channel, duration, URL) is captured for citation and later search. | Creators and researchers convert long videos into skimmable, timestamped notes in one paste, without watching the whole thing or using a paid summarizer. It captures learning from video into a searchable local library. | Technical creator (YouTuber/writer) | • yt-dlp-based local fetch of audio stream and available caption tracks • Caption-first path with fallback to local Whisper transcription • Video metadata capture (title, channel, duration, URL) for citation • Automatic handoff to Notes Builder for structured, timestamped notes • Key-takeaway and section extraction with source timestamps • Indexing of notes and transcript into Global Search • Batch queue for multiple URLs | New src/studio/youtube/ module invokes yt-dlp as a subprocess on a background worker, reusing the transcription and notes modules downstream. Downloads land in the local media directory; transcripts, notes, and video metadata persist to SQLite. Progress streams over IPC; outputs register with the search indexer. Only user-initiated URLs are fetched — no autonomous downloading. | • Audio Transcription • Notes Builder | • yt-dlp breakage from upstream site changes requires periodic updates • Legal/ToS considerations around downloading video content • Long videos strain CPU transcription when captions are unavailable | • Pasting a valid URL fetches audio/captions locally with visible progress • When captions exist they are used; otherwise Whisper transcription runs • Generated notes are sectioned with takeaways linked to source timestamps • Video metadata is captured and displayed as a citation • Notes and transcript are searchable via Global Search • Multiple URLs can be queued and processed sequentially
7 | Notes Builder | Studio | P2 | S-M | 3 | Notes Builder is the summarization and structuring engine of the Studio category: given any input (a transcript, an existing Dobby document, pasted text, or extracted web text), it uses the local LLM to produce well-organized notes with headings, bullet summaries, key takeaways, and optional action items. Users pick a note template (meeting notes, study notes, article summary, decision log) and the model fills it, preserving source references and timestamps where present. Notes live in a dedicated local store, are fully editable in a Markdown editor, and are indexed for Global Search. It is the shared downstream target for Audio Transcription and YouTube to Notes. | Builders convert raw, messy input into structured knowledge they can actually reuse, in seconds, without leaving the app or exposing content to a cloud model. Templates make the output immediately usable. | Product manager | • Multi-source ingestion (transcript, document, pasted text, extracted URL text) • Template-driven structuring (meeting/study/article/decision-log) • Local-LLM generation of headings, summaries, takeaways, and action items • Source-reference and timestamp preservation in output • Markdown editor for post-generation editing • Local note store with tagging and project association • Indexing into Global Search and re-generation with a different template | New src/studio/notes/ module orchestrates local LLM calls via the existing Ollama/llama.cpp client with template prompts stored as versioned assets. Notes persist to SQLite with tags and project links; generation streams over IPC and emits spans to Logs & Traces. Outputs register with the search indexer; templates are extensible. | • Global Search • Logs & Traces | • Summary quality varies with the local model's capability and context window • Long sources may need chunked map-reduce summarization to fit context • Template rigidity may not fit every note type | • Generating notes from a transcript yields correctly structured template output • Long inputs are chunked and summarized without exceeding model context • Generated notes retain source references/timestamps where available • Notes are editable in Markdown and persist across sessions • Notes are searchable via Global Search and taggable • Re-running with a different template produces correspondingly restructured notes
8 | Skill Builder | Automate | P3 | L | 7 | Skill Builder lets users define reusable AI skills: named, parameterized units that bundle a prompt template, an input/output schema, an optional set of allowed tools (e.g. terminal, file read, search), and a target model. Skills are authored in a guided editor with a live test harness that runs the skill against sample inputs and shows the trace. Each skill is versioned and stored in a local manifest so it can be invoked from the Command Center, composed inside Flow Builder, and later published to the Marketplace. This turns one-off prompting into a durable, shareable library of automations. | Builders capture their best prompts and workflows once and reuse them everywhere, instead of retyping prompts. Skills become composable building blocks that grow into a personal automation library. | Product manager | • Guided skill editor with prompt template, input/output schema, and model selection • Declarative tool grants (search, file read, terminal) scoped per skill • Live test harness running the skill on sample inputs with trace output • Semantic versioning and revision history per skill • Local skill manifest registry consumable by Command Center and Flow Builder • Parameter validation against the declared input schema • Export/import of skill definitions for later Marketplace publishing | New src/skills/ module defines a skill manifest schema (JSON) and an executor that binds parameters, enforces tool grants, and calls the local LLM. Skills, versions, and test cases persist to SQLite and a skills directory on disk. Execution emits spans to Logs & Traces and registers actions with Command Center; tool grants integrate with the terminal and search sandboxes. | • Command Center • Logs & Traces • Embedded Terminal | • Over-broad tool grants could let a skill do more than intended • Manifest schema churn breaks previously authored skills without migration • Test harness must faithfully mirror production execution or trust erodes | • A user can define a skill with a prompt, typed inputs/outputs, and model • The test harness runs the skill and shows streamed output plus a trace • Invalid inputs are rejected against the declared schema before execution • Skills are versioned and prior versions remain runnable • A saved skill is invocable from Command Center and selectable in Flow Builder • Tool grants are enforced — a skill cannot use an ungranted tool
9 | Flow Builder | Automate | P3 | L | 8 | Flow Builder is a drag-and-drop canvas where nodes represent skills, document generators, tools (terminal, search, transcription), and control constructs (branch, loop, map, human-approval). Users wire node outputs to inputs to compose multi-step automations, then run them with live per-node status and full traces. A local flow engine executes the DAG, passing typed data between nodes, pausing at approval gates, and persisting run state so flows can resume. Flows are versioned, saved locally, and can be triggered from the Command Center or on a schedule — becoming the automation backbone of the workbench. | Builders assemble repeatable pipelines (e.g. transcribe then notes then generate PRD then scaffold in terminal) visually, without writing glue code. Complex multi-step work runs with one click and full visibility. | Small team lead | • Drag-and-drop node canvas with typed input/output ports and edge validation • Node types for skills, generators, tools, and control flow (branch/loop/map/approval) • Local DAG execution engine with typed data passing between nodes • Live per-node status overlay and full trace integration • Human-in-the-loop approval nodes that pause and resume a run • Flow versioning, save/load, and resumable run state • Triggering from Command Center and (later) on a schedule | New src/flows/ module defines a flow graph schema and a topological execution engine that invokes the skill executor, generators, and tool modules, persisting node/run state to SQLite for resumability. The frontend uses a React flow-graph library for the canvas. Execution emits per-node spans to Logs & Traces; approval nodes gate via the same confirmation pattern as the terminal. Flows register as Command Center actions. | • Skill Builder • Command Center • Logs & Traces • Embedded Terminal | • DAG execution edge cases (cycles, fan-out, partial failure) are hard to get right • Type mismatches between node ports cause confusing runtime failures • Resumable state management grows complex with loops and approvals | • A user can build a multi-node flow by dragging and connecting nodes • Invalid port connections (type mismatch) are rejected at edit time • Running a flow executes nodes in dependency order with typed data passing • An approval node pauses the run and resumes on user confirmation • Per-node status and traces are visible during and after a run • A flow can be saved, reloaded, versioned, and resumed after interruption
10 | Control Center | System | P3 | L | 7 | Control Center is the governance and orchestration hub: it shows all configured agents/skills, their granted tools and permission scopes, which local models are installed and how requests route to them, and every currently running or queued automation. Users can approve or revoke tool grants, set global and per-skill permission policies (e.g. terminal off by default, network denied), pause or kill running flows, and define model-routing rules (which model handles which task class). It centralizes the approval and safety controls that individual features (terminal, skills, flows) enforce, giving one place to see and constrain what autonomous processes may do. | Builders and team leads get one trustworthy place to see and control everything their agents can do and are doing, so autonomy never becomes uncontrolled. It makes running local automations safe and auditable. | Small team lead | • Inventory of agents/skills with their granted tools and permission scopes • Global and per-skill permission policy editing (tool allow/deny, network, fs scope) • Model registry view and routing rules (task class to local model) • Live view of running/queued automations with pause and kill controls • Central approval queue for pending agent-proposed actions • Audit log of permission changes and executed sensitive actions • Emergency stop-all-automations control | New src/control/ module centralizes a permission/policy store (SQLite) that the terminal, skills, and flow executors query before privileged actions, plus a runtime registry of active runs fed by the tracing/event bus. Model routing config maps task classes to Ollama/llama.cpp models. IPC exposes policy CRUD, run control (pause/kill), and the approval queue; changes are audit-logged. | • Logs & Traces • Skill Builder • Flow Builder • Embedded Terminal | • Central policy store becoming a bottleneck or single point of failure • Race conditions between policy changes and in-flight privileged actions • Complexity of routing rules confusing users into misconfiguration | • All skills/agents and their tool grants are listed accurately • Revoking a tool grant blocks that tool in subsequent skill/flow runs • Running automations appear live and can be paused and killed • Model routing rules direct a task class to the configured local model • Pending agent-proposed actions surface in a central approval queue • Permission changes and sensitive actions are recorded in the audit log
11 | Prototype Builder + Test | Generate | P4 | XL | 12 | Prototype Builder turns a Dobby spec (PRD, backlog, or prompt) into a runnable prototype: it scaffolds a project, generates code with the local LLM, installs dependencies and runs a dev server through the sandboxed terminal, and previews the app in an embedded WebView. An iterative generate-run-fix loop uses build/test output and Logs & Traces to self-correct, and an auto-test step generates and runs smoke/UI tests against the preview. The whole loop runs on-device, letting builders go from idea and spec to a clickable, tested prototype without cloud build services. | Founders and developers see their idea running as a real, testable app minutes after specifying it — closing the gap between document and working software entirely on their own machine. | Solo founder | • Spec-to-scaffold generation from PRD/backlog/prompt via local LLM • Dependency install and dev-server launch through the sandboxed terminal • Embedded WebView live preview of the running prototype • Iterative generate-run-fix loop driven by build/test output • Auto-generated smoke/UI tests executed against the preview • Trace-integrated debugging of each generation and fix step • Export of the generated project to disk | New src/generators/prototype/ module orchestrates a generate-run-fix loop that emits code to a project directory, drives installs/dev-server via the Embedded Terminal, and renders the running app in a Tauri WebView; UI tests run via a local headless driver. State and iterations persist to SQLite and emit spans to Logs & Traces. All model calls use the local LLM; nothing is built in the cloud. | • Embedded Terminal • Logs & Traces • Control Center • Flow Builder | • Local models may produce non-building code, making the fix loop slow or stuck • Sandboxing a live dev server and preview securely is complex • Long generate-run-fix loops consume significant local compute and time | • A spec generates a scaffolded project that installs and starts a dev server • The running prototype renders in the embedded preview pane • The generate-run-fix loop uses build errors to attempt corrections • Auto-generated smoke tests run against the preview and report pass/fail • All build commands run through the approval-gated sandboxed terminal • The generated project can be exported to disk and run standalone
12 | Video Generation | Generate | P4 | L | 8 | Video Generation (in Studio/Generate) turns a script, notes, or document into a rendered video: it segments the script into scenes, generates or selects visuals (slides, diagrams, or local image-model frames) per scene, synthesizes narration with a local TTS engine (e.g. Piper), and assembles the timeline with captions using a bundled ffmpeg. Users can preview and re-order scenes, swap voices, and tweak timing before rendering the final MP4. Because rendering, TTS, and assembly all run locally, creators can produce explainer or summary videos without cloud video/voice services. | Technical creators turn written content into publishable video without a studio or cloud render pipeline, cutting production from hours to minutes while keeping full local control. | Technical creator (YouTuber/writer) | • Script/notes-to-scene segmentation via local LLM • Per-scene visual generation or selection (slides, diagrams, local image model) • Local TTS narration with selectable voices (e.g. Piper) • Auto-generated synchronized captions • Scene reordering, timing, and voice adjustment in a timeline editor • ffmpeg-based assembly and MP4 export at selectable resolution • Trace-logged, resumable render jobs | New src/generators/video/ (Studio) module segments scripts via the local LLM, calls a local TTS binary (Piper) and optional local image model for visuals, and assembles output with a bundled ffmpeg on a background render queue. Scenes, assets, and jobs persist to SQLite and a media directory; render progress streams over IPC and emits spans to Logs & Traces. | • Notes Builder • Logs & Traces | • Local image/visual generation quality and speed on consumer hardware • Audio/video sync drift during ffmpeg assembly • Large render jobs consume significant disk and CPU/GPU | • A script is segmented into editable scenes with narration and visuals • Local TTS produces narration audio per scene with a selectable voice • Captions are generated and stay synchronized with narration • Scenes can be reordered and re-timed before rendering • Rendering produces a playable MP4 with synced audio, visuals, and captions • Render jobs are trace-logged and resumable after interruption
13 | Local App Marketplace | Marketplace | P5-P6 | XL | 14 | The Marketplace lets builders extend Dobby by installing packaged skills, flows, and mini-apps. Each package ships a signed manifest declaring its contents, required permissions/tool grants, and compatibility, and installs into a sandboxed plugin runtime governed by Control Center. In P5 the catalog is local-first — install from files, folders, or a local registry, with full permission review before install and one-click enable/disable/uninstall. In P6 it connects to a shared cloud catalog for discovery, publishing, versioned updates, and monetization rails, while keeping installed packages running on-device. This is what turns Dobby from an app into an extensible platform. | Builders get instant capabilities from a growing ecosystem without building everything themselves, and creators can package and share (later sell) their skills and flows. It makes the workbench extensible and community-powered. | Small team lead | • Signed package manifest declaring contents, permissions, and compatibility • Permission review screen shown before install with explicit grant approval • Sandboxed plugin runtime for installed skills/flows/apps, governed by Control Center • Local-first install from file/folder/registry with enable/disable/uninstall • Versioned updates with changelog and rollback • Dependency resolution between packages and Dobby version compatibility checks • P6: shared cloud catalog for discovery, publishing, and monetization rails • Developer SDK and packaging CLI for authoring distributable packages | New src/marketplace/ module defines a package manifest + signature scheme, an installer that verifies signatures and writes into a sandboxed plugin directory, and a runtime loader that registers packaged skills/flows/apps under Control Center permission policies. Local catalog metadata lives in SQLite; P6 adds a cloud catalog client for discovery, publishing, and update checks while execution stays on-device. Packages run sandboxed with only their granted tools. | • Skill Builder • Flow Builder • Control Center • Prototype Builder + Test | • Malicious or over-permissioned packages if sandboxing/signing is weak • Manifest/compatibility versioning across Dobby releases causes breakage • Cloud publishing (P6) introduces trust, moderation, and monetization complexity | • A signed local package installs after an explicit permission-review approval • Installed skills/flows/apps run sandboxed with only their granted tools • Packages can be enabled, disabled, updated, rolled back, and uninstalled • Manifest signature verification rejects tampered or unsigned packages • Dobby-version and dependency compatibility are checked before install • P6 cloud catalog supports discovery and publishing while execution stays local

## Roadmap
6 phases over 12 months. Each phase is independently shippable.
Phase | Name | Months | Theme | Goals | Features | Exit criteria | Person-weeks
P1 | Foundations & Findability | 1-2 | Reshape the app around the 6 categories and make everything findable and observable before adding surface area. | • Ship the categorized, minimal navigation (6 collapsible sidebar groups + global top bar). • Make every artifact discoverable via local semantic + full-text search. • Give a single keyboard-driven entry point (Command Center / ⌘K) to every action. • Make agent/tool runs observable with Logs & Traces. | • Categorized UI redesign • Global Search • Command Center • Logs & Traces | • All existing features reachable through the new 6-category IA with no dead ends. • Search returns relevant local results (semantic + FTS) in under 500ms on a 5k-doc corpus. • 80% of primary actions invokable from ⌘K. • Every agent run produces a viewable trace with tool calls and timings. | 32
P2 | Media & Capture Studio | 3-4 | Turn Dobby into a capture engine: bring audio, video, and web sources on-device and convert them into notes. | • Run a sandboxed, approval-gated terminal for local automation. • Transcribe audio locally with Whisper/STT. • Pull YouTube into transcript + extracted audio + AI notes, fully offline after fetch. • Generate structured AI notes from any captured source. | • Embedded Terminal • Audio Transcription • YouTube → Notes • Notes Builder | • Terminal cannot execute a command without explicit user approval; all runs traced. • Transcription accuracy acceptable on clean speech; runs offline via local model. • A YouTube link yields transcript, audio, and notes in one flow. • Notes Builder ingests audio/YouTube/document sources and outputs editable notes. | 42
P3 | Automation | 5-6 | Let builders author reusable skills, compose them into visual flows, and govern the agents that run them. | • Author, version, and run reusable AI skills. • Compose skills into visual, multi-step automations. • Centralize agent orchestration, permissions, and kill-switches in Control Center. | • Skill Builder • Flow Builder • Control Center | • A user can build a skill once and reuse it across projects and flows. • A multi-step flow executes with visible per-step traces and error handling. • Every agent action is permission-scoped and can be paused/revoked from Control Center. | 49
P4 | Build & Generate | 7-8 | Move from documents and automations to shippable software and rich media. | • Generate app prototypes, preview them live, and test them. • Generate video on-device in the Studio. | • Prototype Builder + Test • Video Generation | • A prototype is generated, previewed, and iterated without leaving Dobby. • Generated prototypes run an automated test loop with reported results. • Video generation produces a shareable clip from a prompt/script on-device. | 54
P5 | Local Marketplace | 9-10 | Make skills, flows, and apps installable and manageable locally, backed by a public SDK. | • Install, update, and manage skills/flows/apps from a local marketplace. • Ship an SDK so builders can package their own skills/flows/apps. • Establish signing, permissions, and sandboxing for installed items. | • Local App Marketplace (install + SDK) | • A user installs a third-party skill/flow/app locally and runs it safely. • Builders can package and locally sideload their own items via the SDK. • Installed items are sandboxed, signed, and permission-scoped. | 39
P6 | Publish & Cloud | 11-12 | Open the marketplace outward: publish, sync across devices, and lay monetization rails — without breaking local-first defaults. | • Publish skills/flows/apps to a shared marketplace. • Optional, encrypted sync across a user's devices. • Monetization rails (paid/free listings, licensing) for publishers. • GA hardening across the whole product. | • Local App Marketplace (publish + cloud) | • A builder publishes an item and another user installs it from the shared marketplace. • Sync is opt-in, end-to-end encrypted, and off by default (local-first preserved). • Publishers can list paid/free items with licensing enforced. • 1.0 quality bar met: crash-free, documented, secured. | 31

## Effort
Effort estimates by feature. Total ~247 person-weeks.
Feature | Category | Phase | Size | Person-weeks | Breakdown (FE/BE/ML/Design/QA, pw) | Key tasks
Categorized UI redesign | Workspace | P1 | M | 10 | frontend 5, backend 1, ml_media 0, design 3, qa 1 | • Design the 6-category sidebar IA and collapsible navigation shell • Build global top bar with Search + Command Center entry points • Migrate every existing route into the new categorized structure behind a flag • Establish shared component/theme system for consistency across new features • Accessibility and keyboard-navigation pass on the new shell
Global Search | System | P1 | M | 7 | frontend 2, backend 3, ml_media 1, design 0, qa 1 | • Build local embeddings index over documents, projects, and notes • Implement hybrid ranking (semantic + SQLite FTS) • Incremental indexing on artifact create/update/delete • Search UI with previews and jump-to-source • Benchmark latency and relevance on a 5k-doc corpus
Command Center | Automate | P1 | M | 6 | frontend 3, backend 1, ml_media 0, design 1, qa 1 | • Build ⌘K palette with fuzzy action search • Create an action registry that features register into • Wire core actions (generate, open, run, navigate) to the palette • Add recent/contextual action suggestions • Keyboard-first UX and shortcut discoverability
Logs & Traces | System | P1 | M | 6 | frontend 2, backend 3, ml_media 0, design 0, qa 1 | • Define a trace schema for agent runs and tool calls • Instrument the existing generation pipeline to emit spans • Persist traces to SQLite with retention controls • Build a run/trace viewer with timings and inputs/outputs • Add filtering by run, feature, and status
Embedded Terminal | System | P2 | M | 9 | frontend 2, backend 5, ml_media 0, design 1, qa 1 | • Spawn sandboxed shell sessions via Tauri with restricted scope • Implement per-command approval gating and audit logging • Stream stdout/stderr to a terminal UI component • Define allow/deny policy and working-directory confinement • Emit terminal actions into Logs & Traces
Audio Transcription | Studio | P2 | M | 10 | frontend 2, backend 3, ml_media 4, design 0, qa 1 | • Integrate local Whisper/STT model with model download/management • Build audio ingest (file upload, mic capture) and format handling • Chunking, diarization stub, and timestamped transcript output • Transcript editor UI with segment navigation • Benchmark accuracy and runtime on CPU/GPU tiers
YouTube → Notes | Studio | P2 | M | 11 | frontend 2, backend 4, ml_media 4, design 0, qa 1 | • Fetch YouTube video + extract audio locally • Reuse transcription pipeline for the extracted audio • Chapter/segment detection and summarization into notes • Handle failures and rate/format edge cases gracefully • End-to-end flow: URL in, transcript + audio + notes out
Notes Builder | Studio | P2 | S-M | 8 | frontend 3, backend 2, ml_media 2, design 0, qa 1 | • Define note templates and structuring prompts • Ingest any source (transcript, document, YouTube) into notes • Editable, linkable notes stored and indexed by Global Search • Summarize, outline, and extract action items • Export notes to Markdown/other formats
Skill Builder | Automate | P3 | L | 15 | frontend 5, backend 6, ml_media 2, design 1, qa 1 | • Define the skill spec (inputs, prompt/logic, tools, outputs, versioning) • Build the authoring UI with test/run and iteration loop • Skill runtime + registry that Command Center and Flows can invoke • Versioning, import/export, and parameter validation • Instrument skill runs into Logs & Traces
Flow Builder | Automate | P3 | L | 16 | frontend 7, backend 5, ml_media 1, design 2, qa 1 | • Build a visual node canvas for chaining skills and tools • Support branching, loops, and data passing between steps • Flow execution engine with per-step retries and error handling • Triggers (manual, scheduled, event) and run history • Per-step trace visibility and debugging
Control Center | System | P3 | L | 13 | frontend 4, backend 6, ml_media 1, design 1, qa 1 | • Central registry of active agents, skills, and flows • Permission model and scoping for agent/tool access • Pause, resume, revoke, and kill-switch controls • Orchestration policies (concurrency, resource limits) • Integrate with Logs & Traces for real-time run oversight
Prototype Builder + Test | Generate | P4 | XL | 30 | frontend 9, backend 9, ml_media 6, design 3, qa 3 | • Generate app prototype code/scaffold from a PRD or prompt • Sandboxed live preview environment inside Dobby • Automated test generation and execution against the prototype • Iterative edit/regenerate loop with diff review • Wire prototype runs and tests into Logs & Traces and Control Center
Video Generation | Generate | P4 | L | 18 | frontend 4, backend 4, ml_media 9, design 0, qa 1 | • Integrate local video generation model(s) and asset pipeline • Script/storyboard-to-video flow in the Studio • Rendering, encoding, and export management • Handle long-running renders with progress and cancellation • Resource/perf management for on-device rendering
Local App Marketplace | Marketplace | P5-P6 | XL | 56 | frontend 16, backend 22, ml_media 2, design 6, qa 10 | • Local install/update/manage of skills, flows, and apps (P5) • Publish an SDK + packaging CLI for third-party builders (P5) • Signing, sandboxing, and permission verification on install (P5) • Publish flow to a shared cloud marketplace with review/moderation (P6) • Opt-in encrypted device sync and monetization/licensing rails (P6)
Hardening/QA/Docs | Cross-cutting | All (P1-P6) | L | 32 | frontend 4, backend 6, ml_media 2, design 2, qa 18 | • Per-phase regression and integration testing across features • Security review of terminal, skills, flows, and marketplace install paths • Performance/perf-budget tracking on-device (search, transcription, render) • User-facing docs, changelogs, and SDK reference • GA/1.0 stabilization: crash reporting, telemetry (opt-in), release checklist

## Team & Resources
Lean team ramping from 3 to 6 over the plan.
Role | Count | Starts | Monthly cost (loaded) | Annual (x count) | Responsibilities
Founder / Product & CEO | 1 | P1 | 12000 | $144,000 | Product vision, roadmap ownership against the 13-feature canon, fundraising, GTM, hiring, design direction, and early developer-community relationships. Takes below-market founder salary to preserve runway; also acts as primary product designer until designer ramps to full-time.
Senior Full-stack Engineer (Tauri 2 / React) | 1 | P1 | 19500 | $234,000 | Owns the desktop shell: Tauri 2 + React app, categorized 6-group navigation redesign, Command Center (⌘K), Global Search UI, Logs & Traces viewer. In later phases builds Skill/Flow Builder UIs, Prototype Builder preview, and the local Marketplace client. Fully-loaded ~$230k/yr (salary + payroll tax + benefits + equipment).
Backend / AI Engineer (Python / FastAPI / LLM) | 1 | P1 | 18500 | $222,000 | Owns FastAPI backend, SQLite data layer, local embeddings + semantic search, agent/tool orchestration and run tracing, sandboxed terminal, and the bring-your-own-model layer (Ollama / llama.cpp integration). Later builds Skill Builder runtime, Flow Builder engine, Control Center (permissions/orchestration), and Marketplace SDK/packaging.
ML / Media Engineer (STT / Video) | 1 | P2 | 18500 | $222,000 | Joins for the Media & Capture Studio phase. Owns local Whisper/STT audio transcription, YouTube -> transcript/audio extraction + Notes, and later local/hybrid video generation in Studio. Optimizes on-device model performance across macOS/Windows/Linux (quantization, Metal/CUDA acceleration).
Product Designer | 1 | P1 | 6500 | $78,000 | Part-time (~2 days/week, contract) through P1-P3 owning the minimal categorized UI system, component library, and interaction design for Command Center, builders, and Marketplace. Converts to full-time (~$13k/mo fully-loaded) in P4 when Prototype Builder and Marketplace surface area expands. Cost shown is the part-time contract rate for P1-P3.
DevRel / Community Lead | 1 | P5 | 15000 | $180,000 | Joins for the Marketplace phases. Seeds and supports the skills/flows/apps ecosystem, writes docs and the publishing SDK guides, runs the developer community (Discord, GitHub, launch content), and drives creator acquisition ahead of the publish/cloud monetization rails.

## Budget
12-month budget. Total $1,134,200 · Ask $2,200,000 (18 mo runway).
Category | Item | Monthly $ | Months | Total $ | Notes
People | Full team (see team.json) - founder, 2 senior engineers from P1, ML/media eng from P2, contract->FT designer, DevRel from P5 | 80167 | 12 | 962000 | Ramps 3.5 FTE-equivalent (P1) -> 6 (P5-P6). Dominant cost by design. Monthly figure is the 12-month average; actual by-phase People spend: P1 $56.5k, P2-P3 $75k, P4 $81.5k, P5-P6 $96.5k.
Infra | CI/CD, code signing/notarization (macOS/Windows), dev & staging infra, error/analytics backend | 800 | 12 | 9600 | Desktop-app distribution keeps this low; code signing certs and cross-platform build runners are the main items.
Infra | Cloud sync + marketplace backend (P6 only) | 3500 | 2 | 7000 | Introduced only at Publish & Cloud phase; usage-metered, opt-in sync. Local-first means this never becomes a per-user cost floor.
Tools | SaaS stack: GitHub, Linear, Figma, Notion, Sentry, 1Password, Slack/Discord, email | 1400 | 12 | 16800 | Per-seat cost grows as team ramps 3.5 -> 6.
Models/Compute | LLM API for evals, golden-set testing, and optional cloud fallback | 400 | 12 | 4800 | Kept minimal because generation runs on-device via bring-your-own-model. Used mainly for regression evals and quality benchmarking.
Models/Compute | GPU cloud for media/video model development (P4-onward) | 3500 | 4 | 14000 | Short-lived rented GPU for STT/video model optimization and quantization; not a runtime cost since inference ships to the user's device.
Legal | Incorporation, IP assignment, contractor/employee agreements, marketplace ToS & privacy, fundraising docs | 1500 | 12 | 18000 | Front-loaded (formation + financing) and again at P5-P6 (marketplace terms, revenue-share, DMCA/content policy).
Marketing | Content, launch (Product Hunt/HN/Show), developer community, creator acquisition, modest paid | 1500 | 12 | 18000 | Deliberately thin early; concentrated in P5-P6 to seed the marketplace supply side alongside DevRel hire.
Contingency | Reserve for hiring slips, comp negotiation, unplanned compute, legal spikes | 7000 | 12 | 84000 | ~8% of operating spend; not allocated to a specific line.

## Market — Competition
Positioning: For builders -- indie developers, solo founders, technical creators, and small privacy-conscious teams -- who are tired of stitching together a costly, cloud-bound stack of AI tools, Dobby is the local-first AI workbench that unifies capture, generation, automation, building, and shipping in one minimal desktop app. Unlike cloud AI IDEs, notetakers, and automation SaaS, Dobby runs your own models on your own machine by default, keeps your data and IP private, and is extensible through an installable marketplace of skills, flows, and apps.
Competitor | Category | What they do | Strengths | Gaps vs Dobby
Cursor | AI IDE | AI-native code editor (VS Code fork) with strong agentic coding, tab completion, and codebase chat. | Best-in-class coding UX, fast iteration, large mindshare, deep IDE integration. | Cloud-model centric (privacy/IP concerns, metered cost), code-only, no local-first guarantee, no capture/media/automation/marketplace, not a cross-domain builder workbench.
Windsurf | AI IDE | Agentic AI IDE with 'Cascade' flows for multi-step coding tasks. | Strong agent flows, polished IDE, enterprise traction. | Cloud-first, code-scoped, no on-device privacy story, no docs/media/notes capture, no local marketplace of skills/flows/apps.
Replit (+ Agent) | agent platform | Cloud IDE and 'Agent' that builds and deploys apps from prompts, hosting included. | Zero-setup, end-to-end build-and-ship in the browser, big education/community base. | Fundamentally cloud-hosted (opposite of local-first), your code lives on their infra, metered usage, no offline/BYO-model, no capture/media studio.
Warp | AI IDE | Modern terminal with AI command generation and agentic workflows. | Excellent terminal UX, AI-in-terminal, growing agent features. | Terminal-scoped, cloud AI by default, no doc-gen/media/automation-canvas/marketplace, not a full builder OS.
LM Studio | local-LLM UI | Desktop app to download, run, and chat with local models; local inference server. | Great model management, fully local, popular with self-hosters, model discovery. | Chat/inference utility only -- no doc generation, automation, capture studio, build tooling, or workflow marketplace; not a builder workbench.
Ollama (and UIs like Open WebUI) | local-LLM UI | Local model runtime + CLI/API; community UIs add chat frontends. | The de facto local inference backbone, huge adoption, simple model pulls, ecosystem. | Infrastructure/plumbing, not an application; UIs are chat-centric; no generate/automate/build/marketplace layer. Dobby can sit on top of Ollama rather than compete.
n8n | automation | Fair-source workflow automation with visual node editor; self-hostable; strong AI/agent nodes. | Powerful, extensible, self-hostable, developer-loved, large integration library. | Automation-only, server/ops-oriented (not a desktop capture-to-ship workbench), no doc-gen/media/prototype tooling, no on-device model-first UX for individuals.
Zapier | automation | Cloud automation connecting thousands of SaaS apps; adding AI agents/actions. | Massive integration catalog, easy for non-technical users, mature marketplace. | Cloud-only, per-task pricing, data flows through their cloud (privacy), no local models, no build/generate/media, aimed at SaaS glue not builders.
Notion AI | notetaker | AI layer over Notion docs/wiki/databases for writing, summarizing, and Q&A. | Ubiquitous workspace, strong docs/knowledge base, smooth AI writing. | Cloud SaaS, your data lives with Notion, no local models, no code/build/automation/media generation, no agent traces or marketplace of executable skills.
Descript | creator tool | Audio/video editing via transcript, AI voices, and clip generation. | Best-in-class transcript-based editing, strong creator following. | Cloud media processing (privacy/cost for unreleased content), media-only, no doc-gen/automation/build, no local-first or BYO-model, no cross-domain workbench.
Raycast | automation | Mac launcher/command palette with extensions, AI, snippets, and a store. | Superb command-palette UX, thriving extension store, developer-beloved, growing AI. | macOS-centric launcher paradigm, AI is cloud-backed, extensions are utilities not agentic flows/apps, no doc-gen/media/build pipeline, no local-model-first stance.
OpenWorker | agent platform | Open-source agent/worker framework for autonomous, tool-using AI tasks. | Open source, agent orchestration primitives, developer extensibility. | Framework/dev-tool rather than a packaged desktop app; no polished capture/generate/media/marketplace product for individual builders; requires assembly.
GPT-based agent apps (ChatGPT desktop, Claude Desktop, custom GPTs) | agent platform | General assistant apps with tools, file upload, code interpreter, and increasingly computer/agent use. | Frontier model quality, huge reach, fast feature velocity, MCP/tool ecosystems. | Inherently cloud + closed-weight, data leaves the device, metered, general-purpose chat rather than a categorized capture-to-ship builder workbench with local models and an installable skills/flows/apps marketplace.

## Milestones
Key delivery milestones across the 12-month plan.
Phase | Month | Milestone
P1 | 1 | New categorized shell live behind a flag
P1 | 1 | Local embeddings index + hybrid search returning results
P1 | 2 | ⌘K palette wired to core actions
P1 | 2 | Run traces visible for existing generation pipeline
P2 | 3 | Sandboxed terminal with per-command approval prompts
P2 | 3 | Local Whisper transcription of an uploaded file
P2 | 4 | YouTube URL → transcript + audio pipeline
P2 | 4 | Notes Builder producing structured notes from transcript
P3 | 5 | Author + save + run a first reusable skill
P3 | 5 | Visual flow chaining 3+ skills with branching
P3 | 6 | Control Center listing agents with permission + pause controls
P3 | 6 | Flow + Skill runs fully visible in Logs & Traces
P4 | 7 | Prototype generation from a PRD with live preview
P4 | 8 | Automated test pass over a generated prototype
P4 | 8 | First end-to-end local video render
P5 | 9 | Install/uninstall a packaged skill locally
P5 | 9 | SDK + packaging CLI v0 published
P5 | 10 | Permission + signature verification on install
P6 | 11 | Publish flow from local package to shared marketplace
P6 | 11 | Opt-in encrypted device sync
P6 | 12 | Monetization + licensing rails live
P6 | 12 | GA / 1.0 release